## Log
Version # | Date Modified | Modified by | Comments
1 | 2015-11-16 | Harshal | Round-1 clarifications raised, (row 8 to row 13)
2 | 2015-11-16 | Tony | Responses for round 1 clarifications (col G&H)
3 | 2015-11-17 | Harshal | Round-2 clarifications raised, (row 14 till row 16)
4 | 2015-11-17 | Tony | #2,7,8,9. I also removed the picture and the extra column for reading ease.
5 | 2015-11-18 | Harshal | More details on #2 and #10 newly added.
6 | 2015-11-18 | Tony
7 | 2015-11-19 | Harshal | Seeking more clarifications on #8 and #9
8 | 2015-11-19 | Tony | Updated #8,9,10 but waiting on Herds team for answers
9 | 2015-11-20 | Tony | Updated #8 and 9
10 | 2015-11-23 | Harshal | #11 till #14 added
11 | 2015-11-23 | Tony | Responded to #10,11,12. #13 and 14 review in progress
12 | 2015-11-24 | Harshal | #11, 12 more details added, Other items status changed as In-Progress
13 | 2015-11-24 | Tony | Updated #13 and 14
14 | 2015-11-25 | Siva | Updated #12, #13, #14 and created #15 for the new report "LicenseNotification".
15 | 2015-11-27 | Siva | #16 added. If possible, please get us more details on #11.
16 | 2015-12-01 | Siva | Updated and closed item #2 and 11.
17 | 2015-12-01 | Tony | #15,16
18 | 2015-12-02 | Siva | Updated #15 and 16.
19 | 2015-12-02 | Tony | Sent review comments to offshore team.
20 | 2015-12-03 | Siva | Feedback/Review comments added from item #17 till 30
21 | 2015-12-03 | Tony | Updated #10, closed #27 (duplicates). Suggest we close #12 (see my note). Updated #23.
22 | 2015-12-04 | Siva | Added #31
23 | 2015-12-07 | Siva | Updated #17,18,19,24,25,26 of the status; Updated #23 further; Closed the item #12.
24 | 2015-12-07 | Tony | Responded to #31 Tech reviewing the rest
25 | 2015-12-08 | Siva | Closed #31 & 10; Updated #23; Updates #20,21,22,28,29,30 os the status;
26 | 2015-12-08 | Tony | #20 - Approved/Closed #23 - Provided clarification Added high-level status
27 | 2015-12-09 | Siva | Updated the status of #23; Updated developers column in the status sheet;
28 | 2015-12-09 | Tony | Revised all report names b/c we have multiple ProgramNotifications Closed 17-19,21,23-26,28,30 Updated 9,22,29 Added 32,33 Added new reports Sent revised spec for ProgramNotifications_CWD Added Common Info tab/removed from specs
29 | 2015-12-10 | Siva | Added #34,35,36,37; Updated #9, 22, 29, 32, 33;
30 | 2015-12-10 | Tony | Updated #34,35,36.
31 | 2015-12-11 | Siva | Closed #34; Updated #35,36;
32 | 2015-12-11 | Tony | Responded to #32,35,36,37 Revised specs for ProgramNotifications_TB and ProgramNotifications_Subreport_CertStatement
33 | 2015-12-14 | Siva | Updated #9, 32, 35, 36, 37; Updated Status sheet of Developer column with assignee.
34 | 2015-12-14 | Tony | Updated 9, 35,36. Working on answers for the rest.
35 | 2015-12-15 | Siva | Updated #32,35,36 of status to in progress; TFS/SQL serverr are not connecting;
36 | 2015-12-15 | Tony | No changes; trying to get answers on outstanding questions
37 | 2015-12-16 | Siva | Updated the status to onshore review of the item #32,33,35,36
38 | 2015-12-16 | Tony | Passed all reports to team for tech review Replied to #9 and 37 Closed 22,29,32,33,35,36 Sent new spec for ConfirmationLetter
39 | 2015-12-17 | Siva | Updated the status for #9; Closed #37; Added #38,39,40;
40 | 2015-12-17 | Tony | Closed #9 Responded to 38,39,40
41 | 2015-12-18 | Siva | Closed #38,39,40; Added #41; Moved the contact info to new sheet;
42 | 2015-12-21 | Tony | Answered #41
43 | 2015-12-22 | Siva | Updated the status of #41 to Onshore review.
44 | 2015-12-22 | Tony | Closed #41.
44 | 2016-01-07 | Siva | Added new row #42,43,44 according to new requirement.
45 | 2016-01-08 | Tony | Replied to 42, 43, 44 Included Screenshots on the 20160108_Screenshots tab
46 | 2016-01-11 | Siva | Closed #42,43; Updated #44;
47 | 2016-01-12 | Dan | Updated #44; Sent new spec for AL_Reports\License_MovementPermitEquine
48 | 2016-01-13 | Siva | Closed #44; Added #45,46,47,48,49.
49 | 2016-01-14 | Siva | Closed #48; Added #50.
50 | 2016-01-15 | Chandra | Closed #50; Added #51, #52
51 | 2016-01-15 | Dan | Sent sample report for font, font size, and margin specifications. Note that the placement of the "remarks" field has been changed in the sample report. Responded to #46, #47, #49, #51, #52
52 | 2016-01-18 | Siva | Closed #46, 47,49, 51,52
53 | 2016-01-20 | Dan | Sent updates for the AL_Reports\License_MovementPermitEquine Added time column in Status page of Herds_Clarifications document. Please list time spent on reports in this area.
54 | 2016-01-21 | Siva | Updated TimeSpent column for all the report in Status page.
55 | 2016-03-08 | Dan | Change request for ProgramCertificate_PEQAP, found in \USAHERDS\src\USAHERDS_Reports2008\pa_reports
56 | 2016-03-09 | Siva | Incorporated the change request and added #53
57 | 2016-03-09 | Dan | Responded to #53
58 | 2016-03-10 | Siva | Updated further to #53
59 | 2016-03-14 | Dan | Updated #53
60 | 2016-03-15 | Siva | Closed #53 as this item is implemented as per the request.

## Herds_Clarifications
| Off-shore |  |  |  |  | On-shore
# | Task/Report | Queries/Questions/Assumptions/Task | Status | Road Blocker? | Date Raised | Clarifications from Tony | Date Clarified | Queries/Questions/Assumptions from Technical Team | Clarifications from Tony | Queries/Questions/Assumptions from Technical Team | Clarifications from Tony | Queries/Questions/Assumptions from Technical Team | Clarifications from Tony
1 | General | Access to the SQL Database. This applicable to for all resources | closed | Yes | 16/11/2015 | Try again. If you still cannot access the db, try creating a host entry with the IP address. | 2015-11-16 | Connecting to DB after tried with Fully qualified name "hdcvs-usaherds.caihdcdev.com\d2008" instead of "hdcvs-usaherds\d2008". | N/A | Both of them have @compaid.com email id. | Please provide those addresses. We do not have them under those names. I will also ask Paul.
2 | General | TFS access for two more resources. Mohan_Kumar@compaid.co.in Nagaraju_Chinnapalle@compaid.co.in | closed | No | 16/11/2015 | Unable to complete until both receive their @compaid.com emails. |  | Both of them have @compaid.com email id. | Please provide those addresses. We do not have them under those names. I will also ask Paul. | Email IDs are mohan_gowda@compaid.com Nagaraju_Chinnapalle@compaid.com | Access requested. Requested again on 11/24
3 | General | VM not ready for Sivaprakasam | closed | Yes | 16/11/2015 | This is Paul Pahwa's responsibility. | 2015-11-16 | Naveen will remind Paul | N/A | VM provided to Sivaprakasam (24/Nov/2015) | N/A
4 | ProgramDrop_CWD | Layout and Formatting: FormattedName and FormattedAddress must fit into the window of a No. 10 size standard envelope. Place name and address in the area between 2.125” and 3.5” from the top of the sheet. -- Please provide more details about this. | closed | No | 16/11/2015 | FormattedName should appear about 2.125 inches from the top of the sheet, then the address is below. These letters will be mailed in envelopes with a hole so the name/address must be placed where it will display through the hole. See picture to the right. | 2015-11-16
5 | ProgramDrop_CWD | Layout and Formatting: Use zero inch margins with 1 inch columns to the left and right - Need more explanation | closed | No | 16/11/2015 | Look at the sample report provided in TFS to see how the margins are 0 inches and the columns are 1 inch. | 2015-11-16
6 | ProgramNotifications_CWD | What if the current date and Expiry date(ExpDate) are equal. Which content to show in that case? | closed | No | 16/11/2015 | If current and exp date are the same, print the "past-due letter" text. | 2015-11-16
7 | General | Sujithra is having very less free space in her VM "C" drive. (as of now it is 1 GB) | closed | Yes | 17/11/2015 | This is complete. | 2015-11-18
8 | ProgramDrop_CWD | When we execute the stored procedure with Null input values, no records are returning. Please provide the proper input parameter values to return the records. | closed | Yes | 17/11/2015 | You should be able to get results by just entering a ProgramParticipantKey (leave other parameters null). The records have values between 2 and 195. Some values that look nice: ProgramParticipantKey: 34 182 You can use ProgramParticipantKey = 205 – this has very long name and address fields, which can be used to make sure margins/text boxes fit on the report. | 2015-11-18 | Are we expecting multiple records for any input value combination? If yes then, what would the grouping field in this report? | Drop letter should always be one at a time. Shouldn't need any grouping.
9 | ProgramNotifications_CWD | When we execute the stored procedure with Null input values, no records are returning. Please provide the proper input parameter values to return the records. | closed | No | 17/11/2015 | NotificationGUID = 84E0533C-4C4F-4A55-B9D1-A09EE5425F2D Another NotificationGUID for the program notification report: 88C1FA3C-FCD2-4A57-B193-056DF33328D7 | 2015-11-18 | As of now we are getting multiple records for each input. For example "84E0533C-4C4F-4A55-B9D1-A09EE5425F2D" is returning 8 records. In this scenario, what would the grouping field in this report? | Group by programparticipantkey. Should make sure that each participant gets its own page, and that each participant fits on a single page. | n/a | New Requirement for groupings. See updated spec (track changes on). | Do we need child grouping for this report? As this report has only cover letter subreport at the top. | The goal is to have the Cover Letter only print once per recipient. That’s why we have a parent group for recipient. The child group will handle each individual program participant inside the recipients parent group. There is currently no test data to make it display.
10 | General | Please arrange business knowledge sharing sessions to India team about the Herds application. This would increase the quality and volume of deliverables | closed | No | 18/11/2015 | Meeting hopefully for Tues/Wed next week. | 2015-12-08
11 | General | As of now dsConfigs data source is not a Shared Data Source. Is it mandatory to use "dsConfig" as Shared Data Source? There is a technical challenge for that. | closed | No | 23/11/2015 | It is not mandatory, but the tech lead suggested using the Use Shared Data Set in the instructions b/c that is what he would do. What is the technical challenge? | 23/11/2015 | In a report both shared and non-shared datasets are not possible. We will analyze further and let you know in a day. If the onshore team already know how to make it work then please share us the details |  | We have addressed this issue and updated with the existing reports which are checked in to TFS as well.(01/12) | N/A
12 | ProgramNotifications_CWD | o Additional Parameters: UserKey (INT, default value is NULL)  IncludeCover (BOOLEAN, default is false)  IncludeHerdList (BOOLEAN, default is false) Is it required to add the above parameters as additional to report? The above parameters are associated to the SP "procRPTNotifications_CWD_Details" | closed | No | 23/11/2015 | The stored procedure procRPTNotifications_CWD_Details does not need those parameters, but USAHerds sends them to the report. You don’t have to link those parameters to the dataset, but they need to be report parameters. The NotificationGUID and ProgramParticipantKey parameters should be automatically created when the dataset is created, but the others (IncludeCover, IncludeHerdList, and UserKey) will need to be manually created for the entire report. | 23/11/2015 | Not able to complete this because of connectivity issue with the VM/VPN | N/A | Onshore technical review. | I think this line item can be closed since each task related to the proc has it's own line item now.
13 | ProgramNotifications_CWD | Draft version of report attached in PDF format. Request to have review and share the feedback | closed | No | 23/11/2015 | 1. Change font for PremiseName, FederalIdentifier/StateIdentifier, PremiseAddress to Courier New. Keep the word "Premises:" in Times New Roman. 2. Remove character returns between "Sincerely" and the image and make the image larger. | 2015-11-24 | New modifications has been incorporated and attached the pdf file for review.
14 | ProgramDrop_CWD | Draft version of report attached in PDF format. Request to have review and share the feedback | closed | No | 23/11/2015 | 1. Change font for PremiseName, PremisesID, PremiseAddress to Courier New. 2. Add the word "Premises:" in Times New Roman above the PremiseName, etc. to match the other reports. 2. Remove character returns between "Sincerely" and the image and make the image larger. | 2015-11-24 | New modifications has been incorporated and attached the pdf file for review.
15 | LicenseNotifications_AnimalDealerHauler | 1. Created initial draft of the report for your review. 2. There is no data to test for "ClassificationType:Backyard Hatchery Permit". | closed | No | 25/11/2015 | 1. In process 2. Use BatchSequence = 9 | 2015-12-01 | 2. Tested with BatchSequence=9 and attached the pdf for review.
16 | LicenseNotifications_AnimalDealerHauler | Request to have review and share the feedback(PDF attached) | closed | No | 27/11/2015 | Eliminate the image of the signature. This report should not have a signature, just a blank space for now. Might add signature later. | 2015-12-01 | Removed the signature part and left it as blank. Attached the pdf for technical review.
17 | ProgramNotifications_CWD | All Text printed should use "None" as formatting for placeholder instead of HTML. Database fields often have New Line characters that do not render when the formatting is set to HTML. | closed | No | 2015-12-02 | N/A
18 | ProgramNotifications_CWD | Premises/Permit information: Use a separate placeholder for each field from the dataset - each placeholder can have different font, so you won't need to put HTML in there to handle the change from Times New Roman to Courier New. | closed | No | 2015-12-02 | N/A
19 | ProgramNotifications_CWD | There is a lot of white space between paragraphs/rows. Put a carriage return at the end of each text block/paragraph for this spacing and then remove the blank rows from the table. | closed | No | 2015-12-02 | N/A
20 | ProgramDrop_CWD | Text Change: If you believe you have received this letter in error, please call our office. -- phone number is included in header, so we won't print it on the report. (new change based on recent customer meeting) | closed | No | 2015-12-02 | Approved | 2015-12-08
21 | ProgramDrop_CWD | Change the layout to the table-based layout in SampleReport/ProgramDrop_Generic and the CWD Notification. | closed | No | 2015-12-02 | N/A
22 | ProgramDrop_CWD | Add a grouping to the table. ds1 should be the dataset for the main table, and we want to group by ProgramParticipantKey. This way, you won't have to use =First(Fields!whatever.value, "ds1") for every database field. See ProgramDrop_Generic for reference | closed | No | 2015-12-02 | Change the grouping to use ProgramParticipantKey and PremiseKey – if there are multiple premises on a program, you should get multiple pages, with a different premises listed on each page. (Test data: ProgramParticipantKey = 12). | 2015-12-09 | Changes has been incorported and attached pdf in the mail for onshore technical team review.
23 | ProgramNotifications_CWD | Tony forgot to include additional text in the original spec. A revised spec will be sent tomorrow, 12/03 | closed | No | 2015-12-02 | I only have a hard copy and I left it at the office. Expect revised spec on 12/04. Apologies. | 2015-12-03 | If you are busy, please send us the scanned copy of the requirement. So, we try to understand and incorporte the changes. | Scanned copies sent. Only changes were the text below the ----- line. The recipient will cut this off and mail in. | We are assuming this changes is only for ProgramDrop_CWD report. We have incorported as your comments and attached initial draft version for your review. | I made another mistake. This was for ProgramNotifications, not ProgramDrop. Please remove the text from ProgramDrop and add it to the ProgramNotifications.
24 | ProgramNotifications_CWD | Text does not toggle properly. The condition is comparing formatted dates, which means it's comparing alphabetical order by Month (so April 2016 is before December 2015). Just compare ExpDate and Today() directly, not formatted versions of those fields. | closed | No | 2015-12-02 | N/A
25 | ProgramNotifications_CWD | Text change: rather than use one expression with a big IIF statement and html tags for text emphasis, please refer to programDrop_Generic as a sample of how this text can be added. Note that the condition to toggle the text is set on the Row Visibility property of the entire row. Highlight the entire row and right click on the left-side buffer. DO NOT use the F4 properties for the row/textbox, as this will add extra whitespace to the text | closed | No | 2015-12-02 | N/A
26 | ProgramNotifications_CWD | The sample report uses ProgramKey to determine visibility. Use a date comparison (expdate and today) instead | closed | No | 2015-12-02 | N/A
27 | General | Meeting with the Project Manager and Technical Lead Tuesday or Wednesday of next week | closed | No | 2015-12-02 | Duplicate of #10 | 2015-12-03
28 | ProgramDrop_CWD | All Text printed should use "None" as formatting for placeholder instead of HTML. Database fields often have New Line characters that do not render when the formatting is set to HTML. | closed | No | 2015-12-02 | N/A
29 | ProgramDrop_CWD | Premises/Permit information: Use a separate placeholder for each field from the dataset - each placeholder can have different font, so you won't need to put HTML in there to handle the change from Times New Roman to Courier New. | closed | No | 2015-12-02 | Change the reference to [PremiseIDs] to [FormattedPremisesID], which is a new field on the dataset. if you don't see it, refresh the fields for ds1. | 2015-12-09 | Changes has been incorported and attached pdf in the mail for onshore technical team review.
30 | ProgramDrop_CWD | There is a lot of white space between paragraphs/rows. Put a carriage return at the end of each text block/paragraph for this spacing and then remove the blank rows from the table. | closed | No | 2015-12-02 | N/A
31 | LicenseNotifications_AnimalDealerHauler | Wrong signature. I don't believe I specified what to use, and we were just going to go with a blank/placeholder image. I have created a placeholder image, and changed dsConfigs to point to that. Please ask team India to get latest version and use First(Fields!DADH_SignatureFilename.Value, "dsConfigs") as the value for the image. Make sure that the text is not stretched (Sizing should still be FitProportional like it was before) --Ques: We are getting the signature if we use the filed DADH_SignatureFileName as per this comment. So, we are assuming that if that fields gives value as signature then it signature should present for this report. Please confirm. | closed | No | 2015-12-04 | The placeholder signature is the name in a script font. This is acceptable for now. | 2015-12-08
32 | ProgramNotifications_CWD | n/a | closed | No | 2015-12-09 | New requirement: Add the CoverLetter subreport. See revised spec (track changes on). |  | The revised spec is mentioned that "as part of the parent group, add a subreport" but not having the details about where exactly to be added the subreport in the main report. Meaning- is that next to the header? If yes, how about the report alignment, when 1 report goes to 2 pages then how about footer/header. | The Cover Letter subreport should be on it's own page and appear first, before the main report. If one report goes to two pages, then header/footer should repeat, but none of these reports should go to two pages. | Will this Cover Letter subreport has any header/footer or with out that? | Yes, the header/footer should appear and be inherited from the main report. See the sample in the CertStatement spec.
33 | ProgramNotifications_CWD | n/a | closed | No | 2015-12-09 | The Row Visibility conditions are backwards. Conditions should evaluate to true when the field should be hidden.
34 | General | There are columns which are not matching with the exact name b/w the spec and SP. However, we are assuming those columns depends on the similar name. Some of them specified here, PremiseKey in Spec but PremiseID in SP, PremName-->PremisesName & PremAdrress --> PremiseAddress. Please clarify. | closed | No | 2015-12-10 | Correct, the values are similar, just abbreviated. | 2015-12-10
35 | ProgramNotifications_TB | 1. There is no test data available to test. 2. For the subreport mentioned that "At bottom of child grouping (make sure it prints on a new page)" how about footer/header. | closed | No | 2015-12-10 | 1. TBD 2. Yes. See the sample in the subreport spec. | 2015-12-10 | 2. For the subreport(Cover Letter), how would be the report look like after integrating with main report. Will this print on new page without header/footer? | The Cover Letter subreport should be on it's own page and appear first, before the main report. | 1. Any update about the Test Data for Stored Proc to return? 2. Will both the Cover Letter/CertStatement subreport has any header/footer or with out that? | 1. NotificationGUID = ‘36AEA9FA-48FB-4E1B-A81F-ADD1A11EFCE3’ ProgramParticipantKeys: 201,207 2. Yes, the header/footer should appear b/c they are inherited from the main report. Please see the sample in the CertStatement.
36 | ProgramNotifications_Brucellosis | 1. There is no test data available to test. 2. For the subreport mentioned that "At bottom of child grouping (make sure it prints on a new page)" how about footer/header. | closed | No | 2015-12-10 | 1. TBD 2. Yes. See the sample in the subreport spec. | 2015-12-10 | 2. For the subreport(Cover Letter), how would be the report look like after integrating with main report. Will this print on new page without header/footer? | The Cover Letter subreport should be on it's own page and appear first, before the main report. | 1. Any update about the Test Data for Stored Proc to return? 2. Will both the Cover Letter/CertStatement subreport has any header/footer or with out that? | 1. NotificationGUID = ‘E47D085A-3799-4A0E-8CCB-CE0A42C7CE6F’ ProgramParticipantKeys: 206,197,199,203 2. Yes, the header/footer should appear b/c they are inherited from the main report. Please see the sample in the CertStatement.
37 | ProgramNotifications_Subreport_CertStatement | What would be the exact value for the dynamic field "ProgramDisplayText" from the main report. B/c in the spec for the subreport, in the test data section mentioned dynamic field with "Free Herd"(Certified Brucellosis Free Herd) but in the format section mentioned <<>>Free Herd. So, the word Free Herd will come part of the input field itself or we can hard code in the subreport only. | closed | Yes | 2015-12-10 | The dynamic field values should be "an accredited tuberculosis" and "a certified brucellosis" This is a change to the current DisplayText b/c we have to account for English grammar (a vs. an) so you may have to edit the ProgramDisplayText. Updated spec attached. From tech lead: You can send "a" vs "an" on the main report instead if that is easier. | 2015-12-11 | 1. If we send "an or a" from the main report - when it uses at the sub-report header section, it may not aligned as per the requirement b/c after "AN or A",the rest of the input should come in the next line. 2. From the original query, the word "Free Herd" will come part of the input field itself or we can hard code in the subreport only. | 1. You may move the A/AN to the same line as the display text. 2. Hard code in the subreport. | FYI. We have written function to take care of A&AN in online and rest of the input to the next line as per our earlier requirement in the subreport itself. | n/a
38 | ProgramConfirmationLetter_Generic | As per the spec, it is mentioned like "if both Vet and VMO are NULL". So, do we have to assume "VetName" and "VMOVetName" from dsVetInfo for condition checking. Please confirm. | closed | Yes | 2015-12-17 | Check if those fields are NULL before printing. If VetName is null, do not print that part of the sentence. Same situation with VMO name. | 2015-12-17
39 | ProgramConfirmationLetter_Generic | There is no data from dsVetInfo for testing. | closed | Yes | 2015-12-17 | Tech lead will create more vets and then attach them to the program records so that you can actually see this information. | 2015-12-17
40 | ProgramConfirmationLetter_Generic | As per the spec, its not mentioned the "NotificationGUID" as parameter. But reference given that, the query for list of "NotificationGUID". Without the NotificationGUID value, we are unable to get the data. As ref. mentioned to see ProgramDrop_CWD report. But, in that we used NotificationGUID as a input parameter. | closed | Yes | 2015-12-17 | ProgramConfirmationLetter_Generic will use procRPTGetCertificateData for its dataset. NotificationGUID is not a parameter for that proc. You will just be using ProgramParticipantKey. Refer to the query in the spec and look at the other column – it should have returned a GUID and a ProgramParticipantKey for each participant. | 2015-12-17
41 | ProgramConfirmationLetter_Generic | We are not seeing the below 2 fields in dsConfigs. <dsConfigs.USDAVetName> and <dsConfigs.USDAVetTitle> | closed | Yes | 2015-12-18 | Those fields were not checked in properly. Get latest version and try again. | 2015-12-21
42 | LicenseNotifications_CommercialBreederBroker | Assuming the report would be exported/printed only in pdf. Please confirm | closed | No | 2016-01-07 | Correct. Always PDF. | 2016-01-08
43 | LicenseNotifications_CommercialBreederBroker | We have observed few alginment check in the existing implementation, its like overlapping the "ExecutionTime" field and extra spaces b/w the words. So, should we correct them, as part of this changes? Please confirm. | closed | No | 2016-01-07 | Yes please | 2016-01-08
44 | LicenseNotifications_DomesticAnimalGarbageFeeding LicenseNotifications_MeatEstablishment LicenseNotifications_PoultryTechnician LicenseNotifications_RenderingPlant LicenseNotifications_Taxidermist | As part of the requirment mentioned that "Build report body as table – these reports were built in Reports 2005, before font changes within a textbox was allowed". But, the report is already implemented with report body as table(Tablix) format only. Please confirm, do we have to do any changes part of this point. | closed | Yes | 2016-01-07 | These reports are just free textboxes inside a list (tablix). The tablix in this case is only used to group/repeat the items inside it. We’d like the text inside the tablix changed from free textboxes into a table-based layout, similar to the Alabama letters. | 2016-01-08 | For "LicenseNotifications_DomesticAnimalGarbageFeeding" and "LicenseNotifications_Taxidermist" report has a small table(Tablix) in side the main table(Tablix) currently. Should we merge those table(Tablix) to one with the main body table(Tablix)? Or any specific funtionality associated to it?. As we see there is no funtionality associated to the small tablix. So merged with one main tablix. | So long as the groupings are retained from the two existing tables, the tables can be merged into a single tablix. However, the groupings MUST remain, and they must still display the same way they currently do. The “small table” displays a list of species/animals associated with the license. It will print a single row for each species. (example: license key = 4 will display 2 species)
45 | AL_Reports\License_MovementPermitEquine | As specified in the spec, the field "Formatted Name" and "Formatted Address" are not used in this report. Are these columns are not applicable to this report ? | closed | No | 2016-01-13 | "Formatted Name" and "Formatted Address" are not applicable to this report. It was an error that they were included in the spec document.
46 | AL_Reports\License_MovementPermitEquine | Are these 2 values "Cert. # 15-AL-729471 and Cert.Date 09/04/2015" are constant values? Because, in sample report it looks like both fields are hard coded value. | closed | Yes | 2016-01-13 | The OCVI Cert # is the CertificateNbr field in the dataset. Cert. Date is the CVIDate field in the dataset.
47 | AL_Reports\License_MovementPermitEquine | Following 3 fields are not available in the stored procudure *Vet Phone #* , <Permit Notes> and *Premises #*. Please confirm where do we have to fetch the values for these filelds. | closed | No | 2016-01-13 | VetPhoneNumber, Remarks, and OriginPremisesNbr have been added to the stored procedure. Please refresh the fields on the dataset.
48 | AL_Reports\License_MovementPermitEquine | Report spec specified only show 3 images. Is it fixed that we should show only 3 images? Or howmany images we should display if the datasource has more than 3? Because, the stored proc is returning 5 records. Please confirm. - Updated on 14-Jan,We understand that we need to show only 3 images in sort order. And not needed any clarification on this.Hence, closing it. | closed | No | 2016-01-13 | Only show 3 images even if more are available. Sort order 1 goes on the left, 2 in the middle, and 3 on the right.
49 | AL_Reports\License_MovementPermitEquine | Few of the fields in Vet information like Vet name, etc are available in both stored procedure results as well as shared data sets. So, which fields do we need to refer? | closed | Yes | 2016-01-13 | Use the main dataset procRPTLicense_MovementPermitAnimals to get the vet information.
50 | AL_Reports\License_MovementPermitEquine | We assume, footer is not available for this report. Since, it is not mentioned in the sample report but it is mentioned in the Description/Instruction's in the spec. | closed | No | 2016-01-14 | Footer is available for this report. See comments on Design page of the specs document. If images are present then display first passge shown below. If images are not present then display second passage. Equidae accompanied by an EQUINE EVENT INTERSTATE PASSPORT may move interstate between Alabama, Arkansas, Florida, Georgia, Kentucky, Louisiana, Mississippi, North Carolina, Oklahoma, South Carolina, Tennessee, Virginia, & West Virginia for events or exhibition only. This passport does not allow for the interstate movement of equidae between these twelve states when change of ownership occurs. <OR> Equidae accompanied by an EQUINE EVENT PERMIT may move interstate between Alabama, Florida and Georgia /Alabama, South Carolina and Tennessee for events or exhibition. This permit does not allow for the interstate movement of equidae between these four states when change of ownership occur
51 | AL_Reports\License_MovementPermitEquine | As per the instructions there should be 1 inch margin on either side of the report but sample specs design report having less margin on either side. We design designged the report as per instuction hence the report looking clutter because of less width for content. In addition, the font size in sample veries from 8 to 12 pt of Times New Roman font but we set the font size 12pt throughtout the report as per instuction. To make report much cleaner we need to reduce the maring width on either side. Please can you advice on this margin and font size? Refer draft report attached in the mail | closed | No | 2015-01-14 | See attachment to email email. Follow the margins, font, and font size as closely as possible. Manipulate margins or text size if needed to ensure that reports fit onto a single page.
52 | AL_Reports\License_MovementPermitEquine | Following fields are not available in the stored procudure *Owner Phone number* in stored procedure | closed | No | 2015-01-14 | OwnerPhoneNbr has been added to the stored procedure.
53 | ProgramCertificate_PEQAP | Currently the report is in portrait(8.5X11). Assuming this is the size expected but can be taken a print out on landscape(11X8.5) mode. | closed | No | 2015-03-09 | The report is currently a 5"x8" ratio (top half of a standard sheet of paper). It should fit in roughly a 8" x 10" sheet (standard sheet of paper in landscape mode). There should not be a large blank space at the bottom of the report. | 2015-03-09 | As per our understanding, the report should be made to landscape mode and body should fit in the centre of the page. | The borders for the report need to be fixed so that the report has a uniform border (see PDF). Margins on all side of report should be changed to .5" Certificate should be changed so that it is 7.5" tall x 10" Wide

## Status
Report | Status | Developer | Time Spent (In hrs)
General | n/a | n/a
ProgramDrop_CWD | Tech Review | Nagaraju | 16
ProgramNotifications_CWD | Tech Review | Sivaprakasam S | 16
LicenseNotifications_AnimalDealerHauler | Tech Review | Sivaprakasam S | 16
ProgramNotifications_Subreport_CertStatement | Tech Review | Mohankumar | 6
ProgramNotifications_TB | Tech Review | Nagaraju | 16
ProgramConfirmationLetter_Generic | Assigned | Nagaraju | 16
ProgramNotifications_Brucellosis | Tech Review | Sujithra | 16
LicenseNotifications_CommercialBreederBroker | Assigned | Chandrashekhar | 6
LicenseNotifications_DomesticAnimalGarbageFeeding LicenseNotifications_MeatEstablishment LicenseNotifications_PoultryTechnician LicenseNotifications_RenderingPlant LicenseNotifications_Taxidermist | Assigned | Sujithra | 18
AL_Reports\License_MovementPermitEquine | Assigned | Chandrashekhar | 28
Change Reqest: ProgramCertificate_PEQAP | Assigned | Sivaprakasam S | 6
Please do not edit this column.
This is for Tony's tracking purposes.

## Common Info
Development Tools
Visual Studio | 2013
SQL | 2008 R2 or greater
Other | Install BIDS 2014 (necessary open report solution in VS)
Server/Database
Server Name | hdcvs-usaherds\d2008
IP: 192.168.245.17 if you need to edit host file
Login | usaherds_readonly or Windows authentication
Password | ~USAHERDS!ReadOnly2008
Database | alusaherds
Team Foundation Server
TFS Link | http://hdcvs-tfs:8080/tfs
Path to solution | $/USAHERDS/src/USAHERDS_Reports2008/USAHerds_Reports2008.sln
Project | AL_Reports
Data source | USAHerds_Datasource
Shared Dataset | dsConfigs - contains generic values (vet name, etc.) that will be used on multiple reports.
Instructions
General | o Do not modify any stored procedures. o Report will be optimized for export to PDF.
Layout and Formatting (unless otherwise noted) | o A sample report layout is in the AL_Reports folder in TFS. The file name is SampleLayout.rdl and it is a rough draft of what is required. o FormattedName and FormattedAddress must fit into the window of a No. 10 size standard envelope. Place name and address in the area between 2.125” and 3.5” from the top of the sheet. o Use zero inch margins with 1 inch columns to the left and right. See SampleLayout.rdl. o All text should be 12 pt. Times New Roman (CourierNew for Premises - see samples) o Left text alignment
Images | o Images for the header and the footer are in the AL_Reports folder in TFS. o Use the following image properties when adding the signature to the report

## Contacts
USA Herds - Reports for Alabama
On-shore contact | Anthony | Anthony_Frascella@exchange.compaid.com | 001-7176513091
Project Manager | Naveen | Naveen_Sankar@compaid.co.in | 0091-9739901212
Developers | Harshal Sivaprakasam Sujithra Nagaraju Mohan | Harshal_Vattiparambathu@mail.compaid.com Sivaprakasam_Sundaram@compaid.co.in Sujithra_Rajamani@compaid.co.in Nagaraju_Chinnapalle@compaid.co.in Mohan_Kumar@compaid.co.in | 0091-9731177500 0091-9742961203 0091-8884111462 0091-9738121467 0091-9964156468

## 20160108_Screenshots
The letters that need to be changed look kind of like this:
Each of the text boxes in here are just textboxes lined up next to each other.
We’d like this changed to something similar to the following:
Where all the text/objects in the main part of the report are in a single table. This way, everything is tied to a single control and will be easier to adapt in the future.